## IS 2023
| Schedule of information sessions -2023 | [5 empty] | 18 Provnices | 50 sessions in 16 provinces
50 sessions ( 26 done by PNC team)
24 sessions will be done by NGOs
Province | Information Session Center | Travelling Date | Presentation Date | Time | Returning Date | Presenter | Observer | Working Days includes travelling
Kandal
KD 1 | Tep pranam High School | 2023-01-03 | 1/3 ( AM ) |  |  | PNC | 1
KD 2 | Sereymongkul |  | 1/3 ( PM ) |  |  | PNC
Kampong Speu
KS 1 | Preah Beida Ekreach | 2023-03-03 | 3/3 ( PM ) |  |  | SIM
KS 2 | Slab Leng | 2023-03-03 | 3/3 ( AM )
KS 3 | Boseth | 2023-02-03 | 2/3 ( PM )
Kampot
KP 1 | Hun Sen Trasek Kaong | 2023-06-03 | 6/3 ( PM ) |  |  | PNC
KP 2 | Hun Sen Boeng Preah |  | 7/3 ( AM )
Takeo
TK 1 | Samdach Hun Sen High School | 7/3/ ( PM ) | 8/3/ ( AM ) |  | 2023-10-03 | 2 PNC
TK 2 | Sok Ann Prey Sandek |  | 8/3/ ( AM )
TK 3 | Hun Sen Ang Rokar |  | 8/3/ ( PM )
TK 4 | Sanlong |  | 8/3/ ( PM )
Prey Veng
PV 1 | BRHS Prey Poan High School |  |  |  |  | NGO | Alumni
PV 2 | Kampong Trabek High School
PV 3 | Chamroeun Vichea High School | [6 empty] | 2.5 days
Preah Vihear
PHV 1 | Roveang high school |  |  |  |  | EDM
PHV 2 | Cheasim Tbeng Meanchey
Kampong Chhnang
KC 1 | Kampong Leng High School |  |  |  |  | Go ahead
KC 2 | Soramrtih High school
Battambang
BT 1 | Anlong Vil | 15/3 | 15/3 (PM ) |  | 17/3 | PNC
BT 2 | Sdao Santepheap |  | 16/3 (AM )
Kampong Cham
KCH 1 | Batheay High School | 20/3 | 20/3 (PM ) |  | 22/3 ( PM ) | PNC
KCH 2 | Peamm Chi Korng High School |  | 21/3 ( AM )
KCH 3 | Hun Sen Kchao High School |  | 21/3 ( PM )
KCH 4 | Hun Sen Kang Tranoeng High School |  | 22/3 ( AM )
Tbong Khmom
TK 1 | Hun Sen Prek A Chi High School |  |  |  |  | KAPE
TK 2 | Tonle Bet High School
TK 3 | Char Themy High School
TK 4 | Chea Sim Kandaol Chrum High School
TK 5 | Hun Sen Ponhea Krek High School
Ratanak Kiri
RK 1 | Som Thom | 26/03 | 27/3 ( AM ) |  | 29/3 | PNC
RK 2 | Anteveasekathan |  | 28/3 ( AM )
RK 3 | Samdach Aouv- Samdach M'e |  | 28/3 ( AM )
Preah Sihanouk
PS 1 | Klaing Leu | 2023-03-04 | 3/4 ( PM ) |  | 5/4 PM | PNC
PS 2 | Hun Sen Santepheap |  | 4/4 ( AM )
PS 3 | Krong Sihanouk |  | 4/4 ( PM )
Kampong Thom
KH 1 | Trial |  |  |  |  | NGOs
KH 2 | Orphanage Center of Kg Thom and Kampong Thom high school
Siem Reap
SR 1 | Pouk | 2023-05-04 | 6/4 ( AM ) |  | 6/4 ( PM ) | PNC
SR 2 | Bakong |  | 5/4 ( PM )
SR 3 | Kralanh |  |  |  |  | NGO
SR 4 | 28 Makara
SR 5 | Varin
Phnom Penh
PP | Passerellesnumeriques |  | 8/4 ( AM )
Pursat
PS 1 | Sustainable Cambodia Pursat |  |  |  |  | NGO
PS 2 | Sustainable Cambodia Kravanh
PS 3 | Kandieng
PS 4 | Teachamrath
Banteay Mean Chey + Uddar Meanchey
BMC 1 | EDM - Sisophon |  |  |  |  | NGO

## For selection portal
Schedule of information sessions -2022
ខេត្ត | មណ្ឌលផ្សព្វផ្សាយ | តំណាងផ្សព្វផ្សាយ | កាលបរិច្ឆេត | លេខទូរសព្ទ័
Kandal
K 1 | Hun Sen Kampong Kantout | PNC | 2022-03-02
Kampong Speu
KS 1 | Uddong High School | PNC | 2022-03-02
KS 2 | Tep pranam High School
KS 3 | HS Mongkul Barpith High school | PNC
Takeo
TK 1 | Samdach Hun Sen High School | PNC | 2022-03-10
TK 2 | Sok Ann Prey Sandek |  | 2022-03-10
KP 3 | Hun Sen Angsdok High School |  | 2022-03-09
Kampot
KP 1 | Hun Sen Angsdok High School | PNC
KP 2 | Hun Sen Borivas |  | 2022-03-15
Kep
KP 1 | Hun Sen Chamkadong High School | PNC | 2022-03-16
KP 2 | BRHS Chakriya Vong High School |  | 2022-03-16
Svay Rieng
| Hun Sen Kg Chak High School | PNC | 2022-03-22
| Hun Sen Prosot High School |  | 2022-03-23
Rattanak Kirri
| Anteveasithkathan High School | PNC | 2022-03-30
| Samdach Ov Samdach Mae High School |  | 2022-03-30
Phnom Penh
PP 1 | PSE | PNC
PP 2 | PNC | PNC
Prey Veng
| BRHS Prey Poan High School | Sipar |  | 015 938683
Kampong Trabek High School
Chamroeun Vichea High School
Hun Sen Kg Leav High School
Preah Vihear
|  | EDM |  | 078 579 444
Kampong Chhnang
| Kampong Leng High School | Goahead |  | 069 729006
Soramrith Hihg School
Krong kampong Chhnang High School
Battambang
| Anlong vil high school | BFD |  | 092 947455
Sdao Santepheap
Kampong Cham
| Peamm Chi Korng High School | KAPE |  | 012 521866
Hun Sen Kchao High School
Hun Sen Batheay High School
Krom Preah Mohaleap High School
Tbong Khmom
| Hun Sen Prek A Chi High School | KAPE |  | 012 521866
Tonle Bet High School
Char Themy High School
Chea Sim Kandaol Chrum High School
Kampong Thom
| Trial | Goahead |  | 069 729006
| Orphanage Center of Kg Thom | Orphanage Center
Siem Reap
| Pouk | Peppy |  | 095 775514
Kralanh
28 Makara
Varin
Pursat
| Sustainable Cambodia Pursat | Sustainable Cambodia |  | 089 471402
Sustainable Cambodia Kravanh
Kandieng
Teachamrath
Note on A38: Thaina SEANG: should find one alumini